## Slide 1
1 / 5
CareerConnect — Growth Plan
NxtWave Growth Intern Challenge
🎯 Objective
• Plan 500 unique workshop registrations
• in 7 days with ≤ ₹2,000 budget
•
• Workshop:
• "Build Your First AI Project
• in 60 Minutes"
•
• Organiser: NxtWave (details TBC)
👥 Target Audience
• Final-year engineering students
• All branches welcome
• 2025–2027 graduation cohort
•
• 📌 Key Assumptions
• • Online workshop (free)
• • Date/speaker TBC by organiser
• • Organic channels tested first
• • No guarantee of real execution
⚠️ All targets are proposed — not observed results.

## Slide 2
Growth Channels & Tracking Strategy
2 / 5
📱 WhatsApp
Target: 180 reg.
Code: WHATSAPP01
• College engineering groups
• High reach, trusted source
• Requires admin permission
Tracked via referral code in registration DB
💼 LinkedIn
Target: 100 reg.
Code: LINKEDIN01
• Professional student profiles
• Good for final-year students
• Post + engage with comments
Tracked via referral code in registration DB
✈️ Telegram
Target: 100 reg.
Code: TELEGRAM01
• Active tech communities
• Fast information sharing
• Free to post with permission
Tracked via referral code in registration DB
🏫 Clubs & Referrals
Target: 120 reg.
Code: CAMPUS01
• Student coordinators
• High-trust personal referrals
• Volunteer ambassador model
Tracked via referral code in registration DB
Total proposed: 500 | Overlap buffer: track duplicates via email normalisation

## Slide 3
7-Day Plan & ₹2,000 Budget
3 / 5
📅 Proposed Schedule (not yet executed)
Day 1
Build website, DB, referral system, promotional assets
Day 2
Identify communities, prepare messages, seek admin permission
Day 3
Begin outreach — permitted WhatsApp & Telegram groups
Day 4
Review performance, A/B test messages, optimise channel focus
Day 5
Expand to college clubs and student coordinators
Day 6
Activate referral sharing, send permitted reminders
Day 7
Final push, analyse registrations, prepare report
💰 Budget Allocation
Website & Tools
₹0
Open-source / local
Organic Outreach
₹0
Permission-based
Paid Promotion*
₹1,000
Only after organic test
Contingency
₹1,000
Buffer for changes
TOTAL
₹2,000
Maximum available
*Paid spend only if organic underperforms — test first, spend later.

## Slide 4
CareerConnect — Working Asset
4 / 5
🏠 Home Page
• CareerConnect brand & tagline
• Workshop banner
• Featured opportunities
• CTA buttons
📝 Registration
• 7-field validated form
• Email normalisation & dedup
• Referral code auto-fill
• SQLite persistence
🔗 Referral Tracking
• 4 default codes (CAMPUS01…)
• URL param auto-prefill
• Per-code reg counts
• Shareable message generator
📊 Dashboard
• Live metrics from DB
• Plotly charts (channel, trend…)
• Password-protected
• Proposed vs actual view
📁 CSV Export
• 6 export types
• Full + analytical (no PII)
• Channel & referral perf.
• Campaign metrics summary
🤖 Workshop Page
• Honest unconfirmed details
• FAQ section
• Proposed topics
• Register CTA
Run locally: python -m streamlit run app.py | All 65 automated tests passing

## Slide 5
AI Usage & What I Learned
5 / 5
🤖 AI-Assisted Decisions
1. Database schema design
AI suggested using UNIQUE COLLATE NOCASE on email → adopted for case-insensitive duplicate prevention.
2. Referral code URL param
AI suggested extracting ?ref=CODE from URL and pre-filling the form → implemented; improves user experience.
3. Export BOM encoding
AI flagged that CSV exports need utf-8-sig BOM for Excel compatibility → adopted in all export functions.
❌ AI Suggestion Rejected
What was suggested:
Add an ML-based job recommender that matches student profiles to opportunities using embeddings.
Why rejected:
Adds external ML dependencies, outside challenge scope, risks over-engineering a prototype. Simple search/filter achieves the same goal without complexity.
🔮 With 24 More Hours I Would…
• Test registration with 5–10 real students to find UX friction
• Improve channel attribution (multi-touch) for overlapping audiences
• Add rate limiting and CAPTCHA before any public deployment
• Test A/B message variations on a small WhatsApp pilot group
All AI decisions documented in deliverables/AI_Learning_Notes.md